## Project Planner
Project Planner - COMPARATIVE STUDY OF SENTIMENT ANALYSIS FOR MOVIE REVIEWS
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Comparative Study of Sentiment Analysis for Movie Reviews Research Project | 1 | 30 | 1 |  | 30%
MileStone1: Topic Submission with Dataset | 1 | 6 | 1 | 7 | 100%
Literature Review | 7 | 3 | 8 | 3 | 100%
Document the Content for Research proposal | 10 | 3 | 11 | 2 | 100%
MileStone2: Research Proposal Submission | 12 | 1 | 12 | 1 | 100%
Mid Thesis Call 1 with Supervisor | 13 | 1 | 13 | 1 | 100%
Data preprocessing/Feature Engineering/EDA | 13 | 2 | 13 | 2 | 100%
Mid Thesis Call 2 with Supervisor | 15 | 1 | 15 | 1 | 100%
Build Models with different Embeddings | 16 | 3 | 16 | 3 | 100%
Mid Thesis Call 3 with Supervisor | 19 | 1 | 19 | 1 | 100%
Implement changes as per the feedback | 20 | 1 | 20 | 1 | 100%
Mid Thesis Call 4 with Supervisor | 21 | 1 | 21 | 1 | 100%
Documentation as per the feedback | 21 | 2 | 21 | 2 | 100%
MileStone3: Interim Report Submission | 22 | 1 | 22 | 1 | 0
Final Thesis Call 1 with Supervisor | 23 | 1
Model building experiments | 23 | 2 |  |  | 0%
Final Thesis Call 1 with Supervisor | 25 | 1 |  |  | 0%
explain models using LIME/SHAP | 25 | 1 |  |  | 0%
Final Thesis Call 3 with Supervisor | 26 | 1 |  |  | 0%
Comparative Study | 26 | 1 |  |  | 0%
Final Thesis Call 3 with Supervisor | 27 | 1 |  |  | 0%
Document Outc0mes | 27 | 1 |  |  | 0%
MileStone4: Final Report | 28 | 2 |  |  | 0
MileStone5: Video Presentation | 29 | 1 |  |  | 0